## VES Task Group - template DO NO
Type | Phase | Name | Description
VES-20 | Setup | 00 - Set up this Task Group - Partner PoC | 1. Add the three Evaluators and Squad PjM 2. Add the link to the google drive folder for this evaluation
VES-19 | Setup | 01 - Create Channel in DAS Venture Slack - PdM | 1. Create a slack channel for this Evaluation in the DAS Ventures workspace (NOT in the Cadre workspace) 2. Name the channel v_name-of-venture (good examples would be v_culturous-exchange, v_seattle-humane) 3. Add Evaluators to the slack channel: PdM, SA, UxR, and PjM
VES-21 | Setup | 01 - Add PjM to the Evaluation - Partner PoC | 1. In the Squad Needs section, select the correct Venture, Add a role for Project Manager. Add the person to the PjM role you just created. 2. Add the PjM to the google shared drive for the evaluation. 3. Add PjM to this taskgroup as a Responsible person. 4. Add the PjM to the venture Slack channel 5. Share the link to the Evaluation Contributor Tool with the PjM (note it is currently in development)
VES-28 | Setup | 01 - Create a central place to take collaborative notes - PdM | Create a central Gdoc to take collaborative notes 1. The document should be created in the Google Drive Folder for this Painpoint 2. Ensure each internal evaluators are aware of the expectation of collaborative note-taking during the call. 3. Populate the note taking location with the Venture Evaluation Rubric / Checklist
VES-17 | Setup | 02 - PjM Orientation - PdM | Introduce the PjM to the team in the slack channel for this evaluation (v_name-of-evaluation) Familiarize yourself with our workflow, roles, and work products: Venture Evaluation Workflow here (Miro). Evaluator Role Expectations here. Venture Charter example here. Venture Charter Template here. Venture Evaluation Principles here. Venture Evaluation Tool here. (Intended for Contributors to access Evaluation Taskgroups) Note: The latest Onboarding Documentation can be found in GitBook but contributors may or may not have access?
VES-16 | Cursory | 03 - Cursory evaluation - PdM | Consider the Painpoint against our Venture Evaluation Criteria Add notes to the Collaborative Notes document (in the gdrive, linked in the header for this taskgroup) Compose questions for the Painpoint Discovery Call with the Partner, and include those questions on the Collaborative Notes document. 0. You may want to review the Partner Overview for additional context about this Partner (link in the header) 1. Review the Painpoint Notes in the Partner Interface (link in the header)� 2. Review any documents or meeting recordings in the gdrive folder for this painpoint (link in the header) 3. Review any notes from the Painpoint Meeting. You can find the meeting by going to the Partner Interface (link in the header) and scrolling down to the Meetings section.� AC: All your relevant thoughts are in comments in the Collaborative Notes document, and you have indicated whether the Evaluation should proceed with a Discovery call.
VES-25 | Cursory | 03 - Cursory evaluation - Sol. Arch. | Consider the Painpoint against our Venture Evaluation Criteria Add notes to the Collaborative Notes document (in the gdrive, linked in the header for this taskgroup) Compose questions for the Painpoint Discovery Call with the Partner, and include those questions on the Collaborative Notes document. 0. You may want to review the Partner Overview for additional context about this Partner (link in the header) 1. Review the Painpoint Notes in the Partner Interface (link in the header)� 2. Review any documents or meeting recordings in the gdrive folder for this painpoint (link in the header) 3. Review any notes from the Painpoint Meeting. You can find the meeting by going to the Partner Interface (link in the header) and scrolling down to the Meetings section.� AC: All your relevant thoughts are in comments in the Collaborative Notes document
VES-15 | Cursory | 03 - Cursory evaluation - Research | Consider the Painpoint against our Venture Evaluation Criteria Add notes to the Collaborative Notes document (in the gdrive, linked in the header for this taskgroup) Compose questions for the Painpoint Discovery Call with the Partner, and include those questions on the Collaborative Notes document. 0. You may want to review the Partner Overview for additional context about this Partner (link in the header) 1. Review the Painpoint Notes in the Partner Interface (link in the header)� 2. Review any documents or meeting recordings in the gdrive folder for this painpoint (link in the header) 3. Review any notes from the Painpoint Meeting. You can find the meeting by going to the Partner Interface (link in the header) and scrolling down to the Meetings section.� AC: All your relevant thoughts are in comments in the Collaborative Notes document
VES-22 | Draft Charter | 04 - Charter Creation - PdM | Charter 1. Duplicate template Charter and place in correct folder for this painpoint consideration. 2. Update the Authors section to include the Evaluators. 3. Copy the link to the Charter doc and paste it into the URL Planting section toward the bottom of this taskgroup. Product Requirements Document 1. Duplicate the Template PRD and place in correct folder for this painpoint consideration. 2. Update the Authors section to include the Evaluators. AC: buttons labeled Charter for this Painpoint lead to the correct blank Charter
VES-24 | Discovery | 04 - Synthesize cursory evaluations - PdM | Ensure all three independent evaluations have occurred. Ensure there is alignment on the go/no go decision. Hold a synchronous meeting if need be. If the decision is to reject the painpoint, 0. In the Collaborative Notes, summarize the reasons why the venture was not a good fit. 1. In the Partner Relationships Slack channel, notify Partner Relationships team of the decision to decline the Venture and provide a summary of the reason(s) why. This will likely be a 2-3 sentence summary of the reasons listed in Collaborative Notes, excluding any internal deliberations, and cleaned up to be Partner-facing. Request that Partner Relationships communicate the rejection to the Partner.� 2. Mark this task as Delivered 3. FIRST: Select the partner from the dropdown in the Staffing Needs section. THEN In the Update Venture Status section of this taskgroup, fill in the Reason for Declining Venture field, check the confirmation checkbox, and click the Decline Venture button.� If the decision is to proceed with evaluating the painpoint, 1. Notify the PjM that the Evaluation will proceed, and that they should move forward with scheduling a Painpoint Discovery meeting with the Partner 3. Mark this task Delivered and move onto the next task. AC: Shared decision amongst the Evaluators to proceed with the Evaluation or to decline the Venture
VES-23 | Discovery | 04 - Schedule Painpoint Discovery meeting with partner - PjM / PdM | Coordinate scheduling of call. Adjust the due dates for the "Engage in Initial Pain Point..." tasks for the team to the date of the call. Note: notes during the call should be included in the Collaborative Notes document so that all questions and comments are easily accessible in one place. If desired, notes can be copied into the meeting notes in airtable. AC: Call on all attendees' calendars with video call link. From DAS, attendees should be Evaluators (Contributor PjM and Cadre Research, PdM, & Sol. Arch.)
VES-31 | Draft Charter | 05 - Draft Portion of Charter - PdM | Charter document for this evaluation is linked in the header of this taskgroup. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: PdM sections of the Charter are complete
VES-9 | Draft Charter | 05 - Draft Portion of Charter - Research | Charter document for this evaluation is linked in the header of this taskgroup. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: User Researcher sections of the Charter are complete
VES-14 | Draft Charter | 05 - Draft Portion of Charter - Soln. Arch. | Charter document for this evaluation is linked in the header of this taskgroup. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: Solutions Architect sections of the Charter are complete
VES-18 | Draft Charter | 06 - Create PSI (Problem, Solution, Impact) Statement - PdM | Create the Problem statement that appears on the DAS website. AC: Problem field in the Structuring The Venture section of the Venture Details in airtable.
VES-13 | Draft Charter | 07 - Generate Approx. Squad Makeup - Soln. Arch. | Create approximate squad makeup, focusing on creating an initial list of ideal expertise/skills members of the squad might hold.�On this taskgroup page, select the painpoint from the dropdown then add proposed squad members to the squad need section. All squads should include a User Researcher and a Product Manager AC: Squad makeup of AirTable partner page, set to WIP
VES-30 | Finalize Charter | 09 - Finalize Charter - PdM | Charter completed to satisfaction. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: Signoff from the other two evaluators
VES-29 | Finalize Charter | 09 - Finalize Charter - Research | Make sure that the research sections of the Charter are up to date and fully consistent with other areas. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: no discrepancies between the research findings and the final Charter.
VES-10 | Finalize Charter | 09 - Finalize Charter - Soln. Arch. | Make sure that the Soln. Arch. sections of Charter are up to date. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: no discrepancies between the evaluation findings and the final Charter.
VES-6 | Finalize Charter | 09 - Enable squad PdM - Any | Send squad PdM role to HR for recruiting AC: Squad PdM role is "Moved to recruiting"
VES-7 | Kickoff | 10 - Handoff Eval Charter to Squad PdM - PjM | 1. Evaluators (PdM and UxR) synchronously hand off the venture to the Squad (PdM, PjM, and UxR) in a video call. Solutions Architect should be included at your discretion. You can use the Squad Handoff Call Example Agenda 2. Alert Client of the handoff. AC: Squad PdM, PjM, and UxR have taken responsibility for the Venture. Client has been informed that we have approved their venture, and that it is being handed off to a Squad.
VES-4 | Kickoff | 10 - Activate Venture - PdM | Click Activate Venture Button toward the bottom of this Task Group.
VES-27 | Kickoff | 10 - PdM Orientation - PjM | Introduce the PdM to the team in the slack channel for this evaluation (v_name-of-evaluation) Familiarize yourself with our workflow, roles, and work products: Venture Evaluation Workflow here (Miro). Evaluator Role Expectations here. Venture Charter example here. Venture Charter Template here. Venture Evaluation Principles here. Venture Evaluation Tool here. (Intended for Contributors to access Evaluation Taskgroups) Note: The latest Onboarding Documentation can be found in GitBook but contributors may or may not have access?
VES-5 | Kickoff | 11 - Schedule Introduction call with Partner and PdM - PjM | Schedule a video call to introduce the Squad PdM to the Partner. In the scheduling email, be sure to share that the Venture has been officially approved and is ready to move into the execution phase.
VES-8 | Kickoff | 11 - Enable venture squad list - Any | Allow activation of recruiting AC: Venture record contains list of required roles
VES-26 |  | 12 - Create tasks for Followup Survey and Retro - Research | Create tasks for yourself separate from this task group (note: see team gdrive for documentation) Task 1 Name: Send Survey Description: Send the post-handoff survey to the Squad PdM and Squad PjM. Task 2 Name: Schedule Followup Call (if needed) Description: Determine if a followup call is needed. If the survey respondents identify significant issues with the handoff, major discrepancies between the Charter and the Venture as it is being executed, or if clarification is needed on survey responses that cannot be done via Slack, schedule a followup call to discuss.� Task 3 Name: Schedule a retro Description: Schedule a retrospective with the team of Evaluators (PdM, Solutions Architect, User Researcher). Notify the whole Venture Evaluation Team through Slack in case any others want to attend. Outcomes of the Retro should be shared with the team via slack and/or in the next team call.

## Keelworks
Date | Event | Next step | waited on | notes | scheduling
2025-02-02 | Enter Venture Structure | information gathering | - |  | partner
2025-02-07 | initial meeting. Potential painpoint found (CMS) | information gathering | scheduling | initial meeting with Thomas. Potential painpoint found (CMS) | DAS
2025-02-10 | new painpoint in email | information gathering | partner | Thomas send a correction. Wants to look at LMS, not CMS
2025-02-13 | realized PdM was not on email | information gathering | DAS | Thomas left DAS PdM off email. This caused internal dealy
2025-02-20 | KW tries to find correct contacts | information gathering | partner | Several redirects to different PMs in KW
2025-02-27 | attempt to schedule a call | information gathering | DAS | Finding a meeting time
2025-03-06 | Meeting with LMS PdM and PjM | partner to provide information PRD | scheduling | partner to provide information PRD
2025-03-11 | Partner informed us of need to sign NDA | DAS internal discussion | partner | Vent Eval PdM changed from Adi to Seemi
2025-03-13 | Discussed with Venture eval | Discussion with partner | DAS | Partner NDA requirement is orthogonal to DAS public repo stance
2025-03-18 | Phone call with Thomas to discuss NDA | escalate to leadership | scheduling | Thomas wants to protect the idea behind LMS, not the source code.
2025-03-23 | got call on the agenda | Discussion with partner | scheduling | escalation to management. Need a call between CEOs to hash this out.
2025-04-01 | Phone call with Thomas and Seamus to discuss NDA | Send revised NDA | scheduling | Seamus drafted revised NDA; sent to Thomas
Note on D1: tc={cd1c80ab-5fcb-4eda-8021-f6c25c650103}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a field that shows what was waited on for the time between the current and the previous event (row) in the spreadsheet

## OurWave
Date | Event | Next step | waited on | notes
6/2/2025 | Updated Our Wave Collaborative Notes and Client Overview docs | information gathering | DAS | Baseline context docs refreshed to kick off evaluation
6/5/2025 | SA cursory-eval notes added (architecture, AI feasibility) | information gathering | DAS | Jeff documented tech thoughts; evaluation continues
6/9/2025 | Created #v_our-wave Slack channel and invited team & partner | information gathering | partner | Central comms channel established
6/12/2025 | Eval team flagged timeline / cost as key discovery topics | discussion with partner | DAS | Need partner input on resources & schedule
6/16/2025 | Manisha onboarded as PJM- Welcomed on Slack our-wave channel | scheduling | scheduling | Manisha to coordinate Pain-Point Discovery
6/16/2025 | Launched quick-check Go / No-Go emoji poll | Decision to make | Inputs from team | Team to react with - Yes/May/More clarity needed
6/16/2025 | Sent status-update & inquiry email to Kyle (timeline, resources) | partner response | partner | Asked 3 clarifications for evaluation
6/17/2025 | Kyle replied: targets Oct 1 beta, offers sample docs & modest funding | information gathering | DAS | Partner provided answers; internal review
6/18/2025 | Built grant-writer prototype demo; logged AI cost exploration | information gathering | DAS | Early tech validation
6/21/2025 | Proposed shifting beta to 2nd wk Nov for DAS capacity- Email | partner confirmation | partner | Email sent outlining revised timeline
6/24/2025 | Kyle confirmed November beta acceptable | scheduling | scheduling | Timeline locked; move to discovery
6/25/2025 | Announced GO decision; Manisha to schedule Pain-Point Discovery; Wendy added for UX | scheduling | scheduling | Double UX strength (Kenna + Wendy)
6/25/2025 | Manisha acknowledged; will send calendar invite incl. Wendy & Kenna | scheduling | scheduling | Confirmation message in Slack
7/1/2025 | Calendar invite sent – Pain-Point Discovery set for 7/9 5-5:30 PM CDT | meeting | meeting | Google Meet link & agenda attached
7/3/2025 | Jeff shared Gemini tech-demo (AI grant proposal generator) | information gathering | DAS | Demonstrates feasibility & sparks scope discussion
7/9/2025 | Pain-Point Discovery call with partner (Kyle, Wendy, Kenna, Manisha, Naresh, Jeff) | information gathering | Team discussion | validated pain -points & gather detailed requirements
2025-07-21 | First stand up | Solution discussion. | Kyle response - GPT folder solution | Need to check with Kyle regarding his take on project folder solution in GPT app.
2025-07-28 | Standup- Discussed next steps | reach out to kyle and setup review call with partner. | Triming down and finalising charter by pdm | Trim down charter and setup review call
2025-08-04 | Standup- waiting for kyle's response on venture charter meetingon 9th august | check for approval of charter | Meeting with partner | waiting on Meeting with partner
8/92025 | Venture charter workign agreement meeting | check for approval of charter with financial constraints invovled. | Venture charter to be signed | Venture charter to be signed included financial constraints
2025-08-15 | Finalized financial constraints added venture charter sent to kyle for sign off. | Kyle's Approval | Kyle's Approval | waitnig on Approval
2025-08-18 | Kyle Approved Venture charter | Venture charter approved | Venture charter approved | Schedule a video call to introduce the Squad to the Partner.
Venture Evaluation Done
8/26//205 | JIRA - Created & Intro Task assigned , Github template - intiated | Waiting on PRD to review by team | Waiting on PRD to review by team | Jiraboard created
2025-08-29 | Automatin tool is live, PRD to reviewed by Kyle | Waiting on PRD to review by team | Waiting on PRD to review by team | Few project env setups tasks has accomplished.
2025-09-04 | PRD Externl file shared with Kyle and received approval | Waiting on team meeting for onbaord Full stack and QA | team meeting | Project env setup to be finished on jira and task has to generated with User stories.

## Anything Helps
Date | Event | Next step | waited on | notes
2025-07-09 | AH Slack channel created | Information gathering | DAS
2025-07-17 | Updated Problem statement | Information gathering | DAS | At Cursory evalution
2025-07-20 | Cursory Evaluation Research | Cursory Evaluation Research | DAS | Async team discussion regarding 3 pain points
2025-07-28 | Amber onboarded as PjM | Information gathering | DAS
2025-08-08 | Cursory Evaulation Sync | Meet with partner- Discovery Call | Scheduling | Ready to meet with Partner; have questions compiled for 3 pain points
2025-08-11 | Bhargab onboarded | Onboarding | DAS
2025-08-19 | Pain-Point discovery call for 3 pain-points | Information gathering | Scheduling | Partner came up with new Pain-points, as old pain-points have been addressed. New Pain-points cursory evalution started async.
2025-08-19 | Cursory Evaluation Research | Cursory Evaluation Research | DAS | Team is compiling notes and thoughts from discovery call. Will discuss new plan/feasibility in sync call.
2025-08-21 | Updated AH via email | Evaulation Sync Call DAS Team | DAS | Notified Mike Mathias of plans for the next week
2025-08-26 | Evaulation Sync Call DAS Team | Evaluation Sync Call DAS Team | DAS | Team is compiling notes and thoughts. Bhargab is doing additional research.
2025-09-01 | Sent AH Follow Up Questions | Evaluation Sync Call DAS Team | AH | Mike and Eric sent some thoughts, team reviewing for sync call.
2025-09-02 | Evaulation Sync Call DAS Team | Meet with Partner | DAS | Team compiled and reviewed questions for partner
2025-09-04 | Pain-Point discussion call for 2 pain-points SSO and VCS | Information Gathering & Evaluation Sync Call DAS Team | Scheduling | Continued to define new pain point: Volunteer communication tool. Eric sent over user stories to further define priorities for MVP.
2025-09-10 | Volunteer Interview w AH | Evluation Sync Call DAS Team | Scheduling
2025-09-11 | Evaulation Sync Call DAS Team | Naresh to meet with Seamus | Scheduling | Team uncertain if this project aligns with DAS purposes
2025-09-13 | Evaluation Determined a No-Go | Partner Relationships Team Meet with AH |  | Reasons: Aggressive timeline, mission alignment, technical feasibility, staff augmentation risk
2025-09-15 | Email to AH from DAS declining project | Closed Evaluation

## Spokane Valley
Date | Event | Next step | waited on | notes
2025-11-19 | Introductory Meeting Agenda | DAS & SVCA Intro Meeting |  | https://docs.google.com/document/d/186EvHLO7BtFQcVr19P0cChcTKgz0HC9vM7P5RlXHjzs/edit?usp=drive_link
2025-12-01 | DAS & SVCA Intro Meeting | Venture Charter Review |  | https://docs.google.com/document/d/1pFVQxn2_URIDAKJsS_BWpLs6XB1LVNU5WuU61-Iz6K0/edit?tab=t.0#heading=h.iaukf838sd9w
2026-03-24 | Venture Charter Review | Complete all points | DAS | https://docs.google.com/document/d/1EGFyEnSfelQa7f1-PruL0NuTAQv6asJiV_CFJwDH4HA/edit?usp=sharing
2026-03-30 | Contact Partner for warm (re)-welcome - PjM | Partner response | Partner
2026-04-06 | Complete the UX Review Collaborative Notes - UXR | Collaborative Notes Handoff | DAS
2026-04-06 | All Hands | Team meeting - Planning and Next Steps
2026-04-09 | Painpoint Discovery meeting with partner - PjM / PdM | Update Notes
2026-04-22 | Handoff Eval Charter to Squad PdM - PjM
2026-05-04 | Activate Venture - PdM

## SEAPAX
Date | Event | Next step | waited on | notes
| Evaluation Process Started | Information Gathering | DAS
| Introductory Meeting Agenda | DAS & SEAPAX Intro Meeting
2026-06-19 | DAS & SVCA Intro Meeting | Painpoint Discovery meeting with partner - PjM / PdM |  | https://docs.google.com/document/d/10G1ZV5BIpFCY3DU4PtQ4eiPjYBIZw_nay1IU81ezXg0/edit?tab=t.0
2026-07-03 | Painpoint Discovery meeting with partner - PjM / PdM | Update Notes | Scheduling | https://docs.google.com/document/d/10G1ZV5BIpFCY3DU4PtQ4eiPjYBIZw_nay1IU81ezXg0/edit?tab=t.0
| Feedback from DAS Leadership on potential scope | Update Notes | DAS | https://docs.google.com/document/d/10G1ZV5BIpFCY3DU4PtQ4eiPjYBIZw_nay1IU81ezXg0/edit?tab=t.0
| Tell partner this is not in our wheelhouse | Close Out Evaluation

## PORSESH
Issue Key | Summary | Description | Status | Assignee | Reporter | Priority | Epic / Feature | Created | Updated | Due Date
VES-20 | 00 - Set up this Task Group - Partner PoC | 1. Add the three Evaluators and Squad PjM 2. Add the link to the google drive folder for this evaluation | Done | Lakshmi | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-19 | 01 - Create Channel in DAS Venture Slack - PdM | 1. Create a slack channel for this Evaluation in the DAS Ventures workspace (NOT in the Cadre workspace) 2. Name the channel v_name-of-venture (good examples would be v_culturous-exchange, v_seattle-humane) 3. Add Evaluators to the slack channel: PdM, SA, UxR, and PjM | Done | Lakshmi | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-21 | 01 - Add PjM to the Evaluation - Partner PoC | 1. In the Squad Needs section, select the correct Venture, Add a role for Project Manager. Add the person to the PjM role you just created. 2. Add the PjM to the google shared drive for the evaluation. 3. Add PjM to this taskgroup as a Responsible person. 4. Add the PjM to the venture Slack channel 5. Share the link to the Evaluation Contributor Tool with the PjM (note it is currently in development) | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-28 | 01 - Create a central place to take collaborative notes - PdM | Create a central Gdoc to take collaborative notes 1. The document should be created in the Google Drive Folder for this Painpoint 2. Ensure each internal evaluators are aware of the expectation of collaborative note-taking during the call. 3. Populate the note taking location with the Venture Evaluation Rubric / Checklist | Done | Jeffrey Nakasone | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-17 | 02 - PjM Orientation - PdM | Introduce the PjM to the team in the slack channel for this evaluation (v_name-of-evaluation) Familiarize yourself with our workflow, roles, and work products: Venture Evaluation Workflow here (Miro). Evaluator Role Expectations here. Venture Charter example here. Venture Charter Template here. Venture Evaluation Principles here. Venture Evaluation Tool here. (Intended for Contributors to access Evaluation Taskgroups) Note: The latest Onboarding Documentation can be found in GitBook but contributors may or may not have access? | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-16 | 03 - Cursory evaluation - PdM | Consider the Painpoint against our Venture Evaluation Criteria Add notes to the Collaborative Notes document (in the gdrive, linked in the header for this taskgroup) Compose questions for the Painpoint Discovery Call with the Partner, and include those questions on the Collaborative Notes document. 0. You may want to review the Partner Overview for additional context about this Partner (link in the header) 1. Review the Painpoint Notes in the Partner Interface (link in the header)� 2. Review any documents or meeting recordings in the gdrive folder for this painpoint (link in the header) 3. Review any notes from the Painpoint Meeting. You can find the meeting by going to the Partner Interface (link in the header) and scrolling down to the Meetings section.� AC: All your relevant thoughts are in comments in the Collaborative Notes document, and you have indicated whether the Evaluation should proceed with a Discovery call. | In Progress | Lakshmi | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-25 | 03 - Cursory evaluation - Sol. Arch. | Consider the Painpoint against our Venture Evaluation Criteria Add notes to the Collaborative Notes document (in the gdrive, linked in the header for this taskgroup) Compose questions for the Painpoint Discovery Call with the Partner, and include those questions on the Collaborative Notes document. 0. You may want to review the Partner Overview for additional context about this Partner (link in the header) 1. Review the Painpoint Notes in the Partner Interface (link in the header)� 2. Review any documents or meeting recordings in the gdrive folder for this painpoint (link in the header) 3. Review any notes from the Painpoint Meeting. You can find the meeting by going to the Partner Interface (link in the header) and scrolling down to the Meetings section.� AC: All your relevant thoughts are in comments in the Collaborative Notes document | In Progress | Jeffrey Nakasone | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-15 | 03 - Cursory evaluation - Research | Consider the Painpoint against our Venture Evaluation Criteria Add notes to the Collaborative Notes document (in the gdrive, linked in the header for this taskgroup) Compose questions for the Painpoint Discovery Call with the Partner, and include those questions on the Collaborative Notes document. 0. You may want to review the Partner Overview for additional context about this Partner (link in the header) 1. Review the Painpoint Notes in the Partner Interface (link in the header)� 2. Review any documents or meeting recordings in the gdrive folder for this painpoint (link in the header) 3. Review any notes from the Painpoint Meeting. You can find the meeting by going to the Partner Interface (link in the header) and scrolling down to the Meetings section.� AC: All your relevant thoughts are in comments in the Collaborative Notes document | In Progress | Sean | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-22 | 04 - Charter Creation - PdM | Charter 1. Duplicate template Charter and place in correct folder for this painpoint consideration. 2. Update the Authors section to include the Evaluators. 3. Copy the link to the Charter doc and paste it into the URL Planting section toward the bottom of this taskgroup. Product Requirements Document 1. Duplicate the Template PRD and place in correct folder for this painpoint consideration. 2. Update the Authors section to include the Evaluators. AC: buttons labeled Charter for this Painpoint lead to the correct blank Charter | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-24 | 04 - Synthesize cursory evaluations - PdM | Ensure all three independent evaluations have occurred. Ensure there is alignment on the go/no go decision. Hold a synchronous meeting if need be. If the decision is to reject the painpoint, 0. In the Collaborative Notes, summarize the reasons why the venture was not a good fit. 1. In the Partner Relationships Slack channel, notify Partner Relationships team of the decision to decline the Venture and provide a summary of the reason(s) why. This will likely be a 2-3 sentence summary of the reasons listed in Collaborative Notes, excluding any internal deliberations, and cleaned up to be Partner-facing. Request that Partner Relationships communicate the rejection to the Partner.� 2. Mark this task as Delivered 3. FIRST: Select the partner from the dropdown in the Staffing Needs section. THEN In the Update Venture Status section of this taskgroup, fill in the Reason for Declining Venture field, check the confirmation checkbox, and click the Decline Venture button.� If the decision is to proceed with evaluating the painpoint, 1. Notify the PjM that the Evaluation will proceed, and that they should move forward with scheduling a Painpoint Discovery meeting with the Partner 3. Mark this task Delivered and move onto the next task. AC: Shared decision amongst the Evaluators to proceed with the Evaluation or to decline the Venture | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-23 | 04 - Schedule Painpoint Discovery meeting with partner - PjM / PdM | Coordinate scheduling of call. Adjust the due dates for the "Engage in Initial Pain Point..." tasks for the team to the date of the call. Note: notes during the call should be included in the Collaborative Notes document so that all questions and comments are easily accessible in one place. If desired, notes can be copied into the meeting notes in airtable. AC: Call on all attendees' calendars with video call link. From DAS, attendees should be Evaluators (Contributor PjM and Cadre Research, PdM, & Sol. Arch.) | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-31 | 05 - Draft Portion of Charter - PdM | Charter document for this evaluation is linked in the header of this taskgroup. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: PdM sections of the Charter are complete | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-9 | 05 - Draft Portion of Charter - Research | Charter document for this evaluation is linked in the header of this taskgroup. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: User Researcher sections of the Charter are complete | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-14 | 05 - Draft Portion of Charter - Soln. Arch. | Charter document for this evaluation is linked in the header of this taskgroup. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: Solutions Architect sections of the Charter are complete | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-18 | 06 - Create PSI (Problem, Solution, Impact) Statement - PdM | Create the Problem statement that appears on the DAS website. AC: Problem field in the Structuring The Venture section of the Venture Details in airtable. | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-13 | 07 - Generate Approx. Squad Makeup - Soln. Arch. | Create approximate squad makeup, focusing on creating an initial list of ideal expertise/skills members of the squad might hold.�On this taskgroup page, select the painpoint from the dropdown then add proposed squad members to the squad need section. All squads should include a User Researcher and a Product Manager AC: Squad makeup of AirTable partner page, set to WIP | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-30 | 09 - Finalize Charter - PdM | Charter completed to satisfaction. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: Signoff from the other two evaluators | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-29 | 09 - Finalize Charter - Research | Make sure that the research sections of the Charter are up to date and fully consistent with other areas. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: no discrepancies between the research findings and the final Charter. | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-10 | 09 - Finalize Charter - Soln. Arch. | Make sure that the Soln. Arch. sections of Charter are up to date. Any information gathered in Discovery that does not belong in the Charter (such as hosting requirements, user stories, or feature requests) may be added to the appropriate section in the Product Requirements Document AC: no discrepancies between the evaluation findings and the final Charter. | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-6 | 09 - Enable squad PdM - Any | Send squad PdM role to HR for recruiting AC: Squad PdM role is "Moved to recruiting" | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-7 | 10 - Handoff Eval Charter to Squad PdM - PjM | 1. Evaluators (PdM and UxR) synchronously hand off the venture to the Squad (PdM, PjM, and UxR) in a video call. Solutions Architect should be included at your discretion. You can use the Squad Handoff Call Example Agenda 2. Alert Client of the handoff. AC: Squad PdM, PjM, and UxR have taken responsibility for the Venture. Client has been informed that we have approved their venture, and that it is being handed off to a Squad. | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-4 | 10 - Activate Venture - PdM | Click Activate Venture Button toward the bottom of this Task Group. | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-27 | 10 - PdM Orientation - PjM | Introduce the PdM to the team in the slack channel for this evaluation (v_name-of-evaluation) Familiarize yourself with our workflow, roles, and work products: Venture Evaluation Workflow here (Miro). Evaluator Role Expectations here. Venture Charter example here. Venture Charter Template here. Venture Evaluation Principles here. Venture Evaluation Tool here. (Intended for Contributors to access Evaluation Taskgroups) Note: The latest Onboarding Documentation can be found in GitBook but contributors may or may not have access? | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-5 | 11 - Schedule Introduction call with Partner and PdM - PjM | Schedule a video call to introduce the Squad PdM to the Partner. In the scheduling email, be sure to share that the Venture has been officially approved and is ready to move into the execution phase. | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-8 | 11 - Enable venture squad list - Any | Allow activation of recruiting AC: Venture record contains list of required roles | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure
VES-26 | 12 - Create tasks for Followup Survey and Retro - Research | Create tasks for yourself separate from this task group (note: see team gdrive for documentation) Task 1 Name: Send Survey Description: Send the post-handoff survey to the Squad PdM and Squad PjM. Task 2 Name: Schedule Followup Call (if needed) Description: Determine if a followup call is needed. If the survey respondents identify significant issues with the handoff, major discrepancies between the Charter and the Venture as it is being executed, or if clarification is needed on survey responses that cannot be done via Slack, schedule a followup call to discuss.� Task 3 Name: Schedule a retro Description: Schedule a retrospective with the team of Evaluators (PdM, Solutions Architect, User Researcher). Notify the whole Venture Evaluation Team through Slack in case any others want to attend. Outcomes of the Retro should be shared with the team via slack and/or in the next team call. | To Do |  | Lakshmi Bhattiprolu | Medium | Venture Evaluation Structure